## Main
3743 | Copy this doc and follow the link below for instructions. |  | 36 |  | 9 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | This doc is modified from: http://bit.ly/IGDPD_BDC_Example
2017-11-14 | BurndownChartInstructions |  | Hours | Hours | Hours |  |  | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
Rank | Task | Assn | Est. | Worked | Rem. |  |  | 2017-10-26 | 2017-10-27 | 2017-10-28 | 2017-10-29 | 2017-10-30 | 2017-10-31 | 2017-11-01 | 2017-11-02 | 2017-11-03 | 2017-11-04 | 2017-11-05 | 2017-11-06 | 2017-11-07 | 2017-11-08 | 2017-11-09 | 2017-11-10 | 2017-11-11 | 2017-11-12 | Detailed Information | #
Task Assignments
| Hunter | [25 empty] | 5
1 | Movement/Camera | SL | 2 | 4 | 0 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6
1 | Shooting | SL | 1 | 4 | 0 |  | 1 | 1 | 1 | 0.75 | 0.5 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8
2 | Arrows | SL | 1.5 | 2 | 0 |  | 1.5 | 1.5 | 1.5 | 1.5 | 0.5 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9
3 | Knife | SL | 0.5 |  | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 10
11
| Deer | [25 empty] | 12
1 | Movement/Camera | SL | 2 | 2 | 0 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  | 13
1 | Ramming | SL | 1 | 2 | 0 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 |  | 15
2 | Jumping | SL | 1 | 0.25 | 0 |  | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16
17
| Environment | [25 empty] | 18
1 | Ground | SL | 2 | 2 | 0 |  | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 19
1 | Trees | DF | 0.5 |  | 0 |  | 0.5 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 19
1 | Bushes | DF | 0.5 |  | 0 |  | 0.5 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 20
1 | Boulders | BF | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 21
1 | Cliffs | SL | 2 | 0.5 | 0 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 22
2 | Water Features | SL | 1.5 | 4 | 0 |  | 1.5 | 0.5 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 23
1 | Map Boundaries | SL | 1 | 1 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 24
25
| Title Screen | [25 empty] | 26
3 | Character Selection | DF | 1 | 3.5 | 0 |  | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0.5 | 0 | 0 | 0 | 0 |  | 27
3 | Play Button | DF | 0.5 | 2.5 | 0 |  | 0.5 |  |  |  |  | 1 | 1 | 1 | 1 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0.5 | 0 | 0 | 0 | 0 |  | 28
29
| Keyboard Commands | [25 empty] | 30
1 | WASD and Arrow Keys | SL | 1.5 | 0.5 | 0 |  | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 31
1 | Shift is Crouch | SL | 0.5 | 0.5 | 0 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32
2 | Space is jump | SL | 0.5 | 0.25 | 0 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 33
1 | Left click - Hunter - hold to draw bow and release to shoot | SL | 2 | 3 | 0 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 34
2 | Right click - Hunter - is knife | SL | 1.5 |  | 1.5 |  | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 |  | 35
1 | Left click - Deer - Ram | DF | 1 |  | 1 |  | 1 | [19 empty] | 36 | bar: 2017-10-26 to 2017-11-12
2 | Right click - Deer - Melee | DF | 1 |  | 1 |  | 1 | [19 empty] | 36 | bar: 2017-10-26 to 2017-11-12
| UI | [25 empty] | 37
1 | Health bar | SL | 1 | 4 | 0 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  | 38
3 | Cool down bar for deer attack | DF | 1 |  | 1 |  | 1 | [19 empty] | 39 | bar: 2017-10-26 to 2017-11-12
40
41
| Extra time | [25 empty] | 42
3 | Health pick-ups | BF | 2 |  | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 43
3 | Stamina bar | DF | 2 |  | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 44
4 | Network Multiplayer | SL | 4 | 6 | 0 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 1 | 0 |  | 45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
Sprint Settings – Only change cells with dark gray borders | [7 empty] | 2017-10-26: Workdays |  | 101
| Sean Leonard | SL |  | Start Date | 2017-10-26 |  |  | 2017-10-26: Sun; 2017-10-27: 1; 2017-10-28: 1 |  | 102
| Ben Foley | BF |  | End Date | 2017-11-14 |  |  | 2017-10-26: Mon; 2017-10-27: 1; 2017-10-28: 1 |  | 103
| Devin Fowler | DF | [5 empty] | 2017-10-26: Tue; 2017-10-27: 1; 2017-10-28: 1 |  | 104
|  |  |  | Total Days | 19 |  |  | 2017-10-26: Wed; 2017-10-27: 1; 2017-10-28: 1 |  | 105
|  |  |  | Work Days | 17 |  |  | 2017-10-26: Thu; 2017-10-27: 1; 2017-10-28: 1 |  | 106
[8 empty] | 2017-10-26: Fri; 2017-10-27: 1; 2017-10-28: 1 |  | 107
| All | ALL | [5 empty] | 2017-10-26: Sat; 2017-10-27: 1; 2017-10-28: 1 |  | 108
| Unassigned | [25 empty] | 109
| Days to Look Back for Burndown Velocity | 2 | [24 empty] | 110
Interpreted Data – DO NOT CHANGE ANYTHING HERE | [26 empty] | 111
| Current Hours Remaining |  |  |  |  | Days | 17 | 17 | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 |  | 112
[6 empty] | On-Track Line | 36 | 36 | 33.8824 | 31.7647 | 29.6471 | 27.5294 | 25.4118 | 23.2941 | 21.1765 | 19.0588 | 16.9412 | 14.8235 | 12.7059 | 10.5882 | 8.4706 | 6.3529 | 4.2353 | 2.1176 | 0 |  | 113
114
[6 empty] | Sum | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 |  | 115
| Rank (and not reduced to 0 after today) | [25 empty] | 116
| Rank 1 - The MOST important | 1 |  |  |  | Rank 1 | 18 | 13 | 12.5 | 11.75 | 11.5 | 11.25 | 11 | 9.5 | 6.5 | 6.5 | 6.5 | 6.5 | 5.5 | 3 | 2.5 | 2.5 | 2.5 | 2.5 | 1 |  | 117
|  | 2 |  |  |  | Rank 2 | 7 | 6 | 5.75 | 5.25 | 4 | 3.75 | 3.75 | 3.75 | 3.25 | 3.25 | 3.25 | 3.25 | 3.25 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 |  | 118
|  | 3 |  |  |  | Rank 3 | 7 | 6 | 6 | 6 | 6 | 7.5 | 7.5 | 7.5 | 7.5 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5 | 6.5 | 5.5 | 5.5 | 5.5 | 5.5 |  | 119
|  | 4 |  |  |  | Rank 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 1 | 0 |  | 120
| Rank 5 - The LEAST important | 5 |  |  |  | Rank 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 121
[6 empty] | Sum | 36 | 29 | 28.25 | 27 | 25.5 | 26.5 | 26.25 | 24.75 | 21.25 | 22.25 | 22.25 | 22.25 | 21.25 | 18 | 15.5 | 14.5 | 11.5 | 11.5 | 9 |  | 122
123
[6 empty] | Sean Leonard | 26.5 | 21 | 20.25 | 19.5 | 18 | 17.5 | 17.25 | 15.75 | 12.25 | 12.25 | 12.25 | 12.25 | 11.25 | 8 | 7.5 | 7.5 | 4.5 | 4.5 | 2 |  | 124
[6 empty] | Ben Foley | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 125
[6 empty] | Devin Fowler | 7.5 | 6 | 6 | 5.5 | 5.5 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 6 | 5 | 5 | 5 | 5 |  | 126
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 127
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 128
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 129
[6 empty] | ALL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 130
[6 empty] | Unassigned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 131
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 132
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 133
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 134
135
[5 empty] | Team | 3 | [20 empty] | 136
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 |  | 137
[6 empty] | Average Assigned | 12 | 9.6667 | 9.4167 | 9 | 8.5 | 8.8333 | 8.75 | 8.25 | 7.0833 | 7.4167 | 7.4167 | 7.4167 | 7.0833 | 6 | 5.1667 | 4.8333 | 3.8333 | 3.8333 | 3 |  | 138
[6 empty] | On-Track Line | 12 | 12 | 11.2941 | 10.5882 | 9.8824 | 9.1765 | 8.4706 | 7.7647 | 7.0588 | 6.3529 | 5.6471 | 4.9412 | 4.2353 | 3.5294 | 2.8235 | 2.1176 | 1.4118 | 0.70588 | 0 |  | 139
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.5 |  | 140
141
[7 empty] | 2017-10-25 | 2017-10-26 | 2017-10-27 | 2017-10-28 | 2017-10-29 | 2017-10-30 | 2017-10-31 | 2017-11-01 | 2017-11-02 | 2017-11-03 | 2017-11-04 | 2017-11-05 | 2017-11-06 | 2017-11-07 | 2017-11-08 | 2017-11-09 | 2017-11-10 | 2017-11-11 | 2017-11-12 |  | 142
| Total Hours | 36 | [5 empty] | 17 | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 |  | 143
| Hours 2 Days Ago | 11.5 |  |  |  |  | 36 | 29 | 28.25 | 27 | 25.5 | 26.5 | 26.25 | 24.75 | 21.25 | 22.25 | 22.25 | 22.25 | 21.25 | 18 | 15.5 | 14.5 | 11.5 | 11.5 | 9 |  | 144
| Hours Today | 9 |  |  |  | Burndown Velocity | 2017-11-10: 11.5; 2017-11-11: 10.25; 2017-11-12: 9 |  | 145
| Today | 0 |  |  |  | BDV | 2017-10-25: 1.25 |  | 146
147
148
149
150

## Daily Scrum
2017-11-14 |  | Team Members
Dates |  | Sean Leonard | Ben Foley | Devin Fowler |  | Workday
2017-10-26 | Thu | Done: Terrain editing/Walls Next: More terrain editing Help: | Done: Next: Help: | Done: Worked on trees and bushes Next: Tree and bush scale/rotation Help: | Done: Next: Help: | 1
2017-10-27 | Fri | Done: Terrain Shape Next: Water/Waterfall Help: | Done: Next: Help: | Done: Worked on more trees and bushes Next: Start menu Help: |  | 1
2017-10-28 | Sat | Done: Water/Waterfall Next:Terrain Painting Help: | Done: Next: Help: | Done: Worked on start menu Next: Make menu actually work Help: |  | 1
2017-10-29 | Sun | Done: Terrain Painting Next: Bow/Arrows Help: | Done: Next: Help: | Done: Next: Help: |  | 1
2017-10-30 | Mon | Done: Bow/Arrows (Don't damage yet) Next: Shooting Help: | Done: Next: Help: | Done: Wasd controls, wind, sky Next: models Help: |  | 1
2017-10-31 | Tue | Done: Shooting Next: Attaching camera and bow to hunter Help: | Done: Next: Help: | Done: Next: Help: |  | 1
2017-11-01 | Wed | Done: Attaching camera and bow to hunter Next: Drawing bow Help: | Done: Next: Help: | Done: Made a perimeter fence Next: Make fence solid Help: |  | 1
2017-11-02 | Thu | Done: Made First Person/More Terrain Next: More Terrain Help: | Done: Next: Help: | Done: Made fence solid, worked on menu more Next: Start menu Help: |  | 1
2017-11-03 | Fri | Done: More Terrain Next: Nothing Help: | Done: Next: Help: | Done: Trees solid, Menu mostly operational, created more scenes Next: Help: |  | 1
2017-11-04 | Sat | Done: Nothing Next: Nothing Help: | Done: Next: Help: | Done: Next: Help: |  | 1
2017-11-05 | Sun | Done: Nothing Next: Hunter Movement Help: | Done: Next: Help: | Done: Next: Help: |  | 1
2017-11-06 | Mon | Done: Hunter Movement Next: Deer Movement Help: | Done: Next: Help: | Done: Next: Help: |  | 1
2017-11-07 | Tue | Done: Terraforming/Deer Model/Deer Movement/Deer Health/Arrow Damage Next: Hunter Health/Deer Ramming Help: | Done: Next: Help: | Done: Next: Help: |  | 1
2017-11-08 | Wed | Done: Hunter Health/Hurt by Deer Next: Secondary Attacks Help: | Done: Next: Help: | Done: more trees and menu work Next: Help: |  | 1
2017-11-09 | Thu | Done: Networking Next: Fine-Tuning Networking Help: | Done: Next: Help: | Done: Next: Help: |  | 1
2017-11-10 | Fri | Done: Multiplayer Next: Health Bar Help: | Done: Next: Help: | Done: Nothing really/worked on online menu and health count Next: Help: above things, couldnt figure anything out |  | 1
2017-11-11 | Sat | Done: Health Bar Next: More Damage & Health Work Help: | Done: Next: Help: | Done: Next: Help: |  | 1
2017-11-12 | Sun | Done: Damage & Health Next: Help: | Done: Next: Help: | Done: Next: Help: |  | 1
2017-11-13 | Mon | Done: Next: Help: | Done: Next: Help: | Done: Next: Help: |  | 1
2017-11-14 | Tue | Done: Next: Help: | Done: Next: Help: | Done: Next: Help: |  | 1
2017-11-15 | Wed | Done: Next: Help: | Done: Next: Help: | Done: Next: Help: |  | 1
2017-11-16 | Thu | Done: Next: Help: | Done: Next: Help: | Done: Next: Help: |  | 1