## Main
3743 | Copy this doc and follow the link below for instructions. |  | 77 |  | 23 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | This doc is modified from: http://bit.ly/IGDPD_BDC_Example
2017-12-05 | BurndownChartInstructions |  | Hours | Hours | Hours |  |  | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat
Rank | Task | Assn | Est. | Worked | Rem. |  |  | 2017-11-15 | 2017-11-16 | 2017-11-17 | 2017-11-18 | 2017-11-19 | 2017-11-20 | 2017-11-21 | 2017-11-22 | 2017-11-23 | 2017-11-24 | 2017-11-25 | 2017-11-26 | 2017-11-27 | 2017-11-28 | 2017-11-29 | 2017-11-30 | 2017-12-01 | 2017-12-02 | Detailed Information | #
Task Assignments
| Hunter | [25 empty] | 5
1 | Shooting Cooldown or Drawback Requirement to Shoot | SL | 2 | 0.5 | 0 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Sprinting | SL | 1 | 1 | 0 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Crosshair | SL | 1.5 | 0.5 | 0 |  | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6
2 | Hunter Texture | DF | 4 | 1.5 | 0 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0
2 | Bow Texture | SL | 3 | 0.5 | 0 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 |  | 8
2 | Arrow Texture | SL | 2 | 2 | 0 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
2 | Knife Texture | BF | 2 |  | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 9
3 | Knife | BF | 2 |  | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 10
1 | Hunter Animation | BF | 4 |  | 4 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  | 10
11
| Deer | [25 empty] | 12
1 | Ramming | SL | 2 | 1 | 0 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 13
1 | Hunter Knockback on Hit | BF | 2 |  | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
3 | Secondary Attack | BF | 2 |  | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 15
2 | Deer Texture | DF | 4 | 1 | 0 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 |  | 16
1 | Deer Animation | BF | 4 | 2 | 2 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
17
| Environment | [25 empty] | 18
1 | Fall Damage | SL | 1.5 | 1.5 | 0 |  | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 19
25
| Title Screen | [25 empty] | 26
3 | Integrate Network HUD | SL | 2 | 0.5 | 0 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 27
1 | Take off single player options | DF | 1 | 0.5 | 0 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28
3 | Multiplayer Lobby | SL | 2 | 1 | 0 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 27
29
| Keyboard Commands | [25 empty] | 30
1 | Shift - Hunter - Sprint | SL | 1 | 1 | 0 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32
1 | Control - Hunter - Crouch | DF | 1 | 0.25 | 0 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 33
1 | Esc - Pause | SL | 1 | 2 | 0 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 34
2 | Right click - Hunter - is knife | BF | 1 |  | 1 |  | 1 | [19 empty] | 35 | bar: 2017-11-15 to 2017-12-02
1 | Left click - Deer - Ram | SL | 1 | 1 | 0 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 36
2 | Right click - Deer - Melee | BF | 1 |  | 1 |  | 1 | [19 empty] | 36 | bar: 2017-11-15 to 2017-12-02
| UI | [25 empty] | 37
1 | MiniMap/Tracking System | SL | 5 | 5 | 0 |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 38
1 | Timer | SL | 2 | 0.5 | 0 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 39
2 | Hit Indicator | SL | 2 | 2.5 | 0 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 |  | 40
1 | Implement Menu | DF | 3 | 2 | 0 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Pause Menu | DF | 3 | 4 | 0 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Screen Boundaries | SL | 1 | 1 | 0 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41
| Extra time | [25 empty] | 42
3 | Health pick-ups | ALL | 3 |  | 3 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 43
3 | Stamina bar | ALL | 1 |  | 1 |  | 1 | [19 empty] | 44 | bar: 2017-11-15 to 2017-12-02
4 | Escape Routes? | ALL | 3 |  | 3 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 45
46
1 | Misc Networking Issues | SL | 2 | 17 | 0 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 |  | 47
1 | Sound | SL | 4 | 4 | 0 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 |  | 48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
Sprint Settings – Only change cells with dark gray borders | [7 empty] | 2017-11-15: Workdays |  | 101
| Sean Leonard | SL |  | Start Date | 2017-11-15 |  |  | 2017-11-15: Sun; 2017-11-16: 1; 2017-11-17: 1 |  | 102
| Ben Foley | BF |  | End Date | 2017-12-05 |  |  | 2017-11-15: Mon; 2017-11-16: 1; 2017-11-17: 1 |  | 103
| Devin Fowler | DF | [5 empty] | 2017-11-15: Tue; 2017-11-16: 1; 2017-11-17: 1 |  | 104
|  |  |  | Total Days | 20 |  |  | 2017-11-15: Wed; 2017-11-16: 1; 2017-11-17: 1 |  | 105
|  |  |  | Work Days | 17 |  |  | 2017-11-15: Thu; 2017-11-16: 1; 2017-11-17: 1 |  | 106
[8 empty] | 2017-11-15: Fri; 2017-11-16: 1; 2017-11-17: 1 |  | 107
| All | ALL | [5 empty] | 2017-11-15: Sat; 2017-11-16: 1; 2017-11-17: 1 |  | 108
| Unassigned | [25 empty] | 109
| Days to Look Back for Burndown Velocity | 2 | [24 empty] | 110
Interpreted Data – DO NOT CHANGE ANYTHING HERE | [26 empty] | 111
| Current Hours Remaining |  |  |  |  | Days | 17 | 17 | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 |  | 112
[6 empty] | On-Track Line | 77 | 77 | 72.4706 | 67.9412 | 63.4118 | 58.8824 | 54.3529 | 49.8235 | 45.2941 | 40.7647 | 36.2353 | 31.7059 | 27.1765 | 22.6471 | 18.1176 | 13.5882 | 9.0588 | 4.5294 | 0 |  | 113
114
[6 empty] | Sum | 77 | 77 | 77 | 77 | 77 | 77 | 77 | 77 | 77 | 77 | 77 | 77 | 77 | 77 | 77 | 77 | 77 | 77 | 77 |  | 115
| Rank (and not reduced to 0 after today) | [25 empty] | 116
| Rank 1 - The MOST important | 1 |  |  |  | Rank 1 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 26 | 21 | 21 | 12 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 |  | 117
|  | 2 |  |  |  | Rank 2 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 15 | 8 | 8 | 4 |  | 118
|  | 3 |  |  |  | Rank 3 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  | 119
|  | 4 |  |  |  | Rank 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 120
| Rank 5 - The LEAST important | 5 |  |  |  | Rank 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 121
[6 empty] | Sum | 77 | 77 | 77 | 77 | 77 | 77 | 77 | 60 | 55 | 55 | 42 | 40 | 40 | 40 | 40 | 36 | 29 | 29 | 23 |  | 122
123
[6 empty] | Sean Leonard | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 20 | 15 | 15 | 9 | 9 | 9 | 9 | 9 | 9 | 6 | 6 | 0 |  | 124
[6 empty] | Ben Foley | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 |  | 125
[6 empty] | Devin Fowler | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 15 | 15 | 15 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 |  | 126
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 127
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 128
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 129
[6 empty] | ALL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 130
[6 empty] | Unassigned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 131
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 132
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 133
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 134
135
[5 empty] | Team | 3 | [20 empty] | 136
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77 |  | 137
[6 empty] | Average Assigned | 23.3333 | 23.3333 | 23.3333 | 23.3333 | 23.3333 | 23.3333 | 23.3333 | 17.6667 | 16 | 16 | 11.6667 | 11 | 11 | 11 | 11 | 9.6667 | 7.3333 | 7.3333 | 5.3333 |  | 138
[6 empty] | On-Track Line | 25.6667 | 25.6667 | 24.1569 | 22.6471 | 21.1373 | 19.6275 | 18.1176 | 16.6078 | 15.098 | 13.5882 | 12.0784 | 10.5686 | 9.0588 | 7.549 | 6.0392 | 4.5294 | 3.0196 | 1.5098 | 0 |  | 139
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 |  | 140
141
[7 empty] | 2017-11-14 | 2017-11-15 | 2017-11-16 | 2017-11-17 | 2017-11-18 | 2017-11-19 | 2017-11-20 | 2017-11-21 | 2017-11-22 | 2017-11-23 | 2017-11-24 | 2017-11-25 | 2017-11-26 | 2017-11-27 | 2017-11-28 | 2017-11-29 | 2017-11-30 | 2017-12-01 | 2017-12-02 |  | 142
| Total Hours | 77 | [5 empty] | 17 | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 |  | 143
| Hours 2 Days Ago | 29 |  |  |  |  | 77 | 77 | 77 | 77 | 77 | 77 | 77 | 60 | 55 | 55 | 42 | 40 | 40 | 40 | 40 | 36 | 29 | 29 | 23 |  | 144
| Hours Today | 23 |  |  |  | Burndown Velocity | 2017-11-30: 29; 2017-12-01: 26; 2017-12-02: 23 |  | 145
| Today | 0 |  |  |  | BDV | 2017-11-14: 3 |  | 146
147
148
149
150

## Daily Scrum
2017-12-05 |  | Team Members
Dates |  | Sean Leonard | Ben Foley | Devin Fowler |  | Workday
2017-11-15 | Wed |  | Done: Next: Help: | Done: Next: Help: | Done: Next: Help: | 1
2017-11-16 | Thu | Done: Nothing Next: Nothing Help: | Done: Next: Help: | Done: Next: Help: |  | 1
2017-11-17 | Fri | Done: Nothing Next: Nothing Help: | Done: Next: Help: | Done: Next: Help: |  | 1
2017-11-18 | Sat | Done: Nothing Next: Nothing Help: | Done: Next: Help: | Done: Next: Help: |  | 1
2017-11-19 | Sun | Done: Nothing Next: Nothing Help: | Done: Next: Help: | Done: Next: Help: |  | 1
2017-11-20 | Mon | Done: Nothing Next: Shooting Cooldown Help: | Done: Next: Help: | Done: Next: Help: |  | 1
2017-11-21 | Tue | Done: Shooting Cooldown, Crosshair, Sprinting, Fall Damage, Ramming Next: Minimap Help: | Done: Next: Help: | Done: Next: Help: |  | 1
2017-11-22 | Wed | Done: Minimap, Pausing Next:Nothing Help: | Done: Next: Help: | Done: Next: Help: |  | 1
2017-11-23 | Thu | Done: Nothing Next: Timer Help: | Done: Next: Help: | Done: Next: Help: |  | 1
2017-11-24 | Fri | Done: Timer, Lobby, Main Menu Next: Nothing Help: | Done: Next: Help: | Done: Next: Help: |  | 1
2017-11-25 | Sat | Done: Nothing Next: Minimap Arrow Help: | Done: Next: Help: | Done: Working on deer animation Next: Help: |  | 1
2017-11-26 | Sun | Done: Minimap Arrow, Network Lobby Manager Tweaks Next: Tracking System Help: | Done: Next: Help: | Done: reimplemented start menu Next: Help: |  | 1
2017-11-27 | Mon | Done: Minimap Enemy Dots, More Network Lobby Manager Tweaks Next: Help: | Done: Next: Help: | Done: Next: Help: |  | 1
2017-11-28 | Tue | Done: Trying to Fix Arrows Over Network Next: Nothing Help: | Done: Next: Help: | Done: Next: Help: |  | 1
2017-11-29 | Wed | Done: Nothing Next: Continue Trying to Fix Arrows Over Network Help: | Done: Next: Help: | Done: Next: Help: |  | 1
2017-11-30 | Thu | Done: Arrows Fixed! Next: Nothing Help: | Done: Next: Help: | Done: Hunter texture Next: Help: |  | 1
2017-12-01 | Fri | Done: Nothing Next: More Arrow Work, Arrow Texture Help: | Done: Next: Help: | Done: Lots of pause menu work and deer textures Next: Help: |  | 1
2017-12-02 | Sat | Done: Arrow Texture Next: Sound? Help: | Done: Next: Help: | Done: Next: Help: |  | 1
2017-12-03 | Sun | Done: Hit Markers, Sound Next: WinText Help: | Done: Next: Help: | Done: Next: Help: |  | 1
2017-12-04 | Mon | Done: Nothing Next: Strafing, misc bugs Help: | Done: Next: Help: | Done: Next: Help: |  | 1
2017-12-05 | Tue | Done: Strafing, misc bugs Next: Play testing! Help: | Done: Next: Help: | Done: Next: Help: |  | 1